## Story Tracker
Phase 1A – Project & Infra Setup
Sr No | Phase | Story | Assignee | Progress | Status | Ref Document | Date started | Date Completed | Git Push Message / Date
1 | 1A | Setup Git repository and base Spring Boot parent project | Abhijeet | 100% | Done |  | 2026-01-24 | 2026-01-24 | Initial Push
2 | 1A | Create multi-module Maven/Gradle structure for all microservices | Abhijeet | 100% | Done |  | 2026-01-24 | 2026-01-24 | Initial Push
3 | 1A | Add api-gateway module with basic routing | Abhijeet | 100% | Done |  | 2026-01-25 | 2026-01-25 | Initial Push
4 | 1A | Add config-server module | Abhijeet | 0% | Backlog |  | 2026-01-25 | 2026-01-25 | Initial Push
5 | 1A | Add service-registry (Eureka Server) module | Abhijeet | 100% | Done |  | 2026-01-25 | 2026-01-25 | Initial Push
6 | 1A | Add user-service, post-service, message-service, job-service skeletons | Abhijeet | 70% | Partially Done |  | 2026-01-25 | 2026-01-25 | Initial Push
Phase 1B – Config Server & Service Discovery
7 | 1B | Centralize application.yml using Spring Cloud Config | Abhijeet | 0% | Backlog
8 | 1B | Setup Git-based config repository | Abhijeet | 0% | Backlog
9 | 1B | Register all microservices with Eureka Server | Abhijeet | 0% | Backlog
10 | 1B | Validate service discovery and health checks | Abhijeet | 0% | Backlog
PHASE 2: UserService
11 | 2 | Implement user registration API | Abhijeet | 100% | Done
12 | 2 | Implement login API | Abhijeet | 100% | Done
13 | 2 | Generate JWT on successful authentication | Abhijeet | 100% | Done
14 | 2 | Add BCrypt password encryption | Abhijeet | 100% | Done
15 | 2 | Secure APIs using JWT filter | Abhijeet | 100% | Done
16 | 2 | Integrate Google OAuth login | Abhijeet | 50% | Partially Done
17 | 2 | Map OAuth user to local user entity | Abhijeet | 50% | Partially Done
18 | 2 | Handle first-time OAuth user registration | Abhijeet | 50% | Partially Done
19 | 2A | Extend user profile with experience, education & certifications | Abhijeet | 100% | Done
20 | 2A | Implement CRUD APIs for user profile | Abhijeet | 100% | Done
21 | 2A | Add service layer for profile management | Abhijeet | 100% | Done
22 | 2A | Expose API to fetch complete user profile | Abhijeet | 50% | In Progress |  | 2026-02-11 |  | 2A-AddUserDetails Added | Add User Details Added, Other Crud operation is in progress
23 | 2 | Create roles table and seed default roles | Abhijeet | 0% | Backlog
24 | 2 | Map roles to users | Abhijeet | 0% | Backlog
25 | 2 | Implement send connection request API | Abhijeet | 0% | Backlog
26 | 2 | Implement accept/reject connection API | Abhijeet | 0% | Backlog
27 | 2 | Build connection graph logic | Abhijeet | 0% | Backlog
PHASE 3: PostService
28 | 3 | Implement create post API
29 | 3 | Fetch feed based on user connections
30 | 3 | Apply privacy filters on posts
31 | 3 | Implement like post API
32 | 3 | Implement comment on post API
33 | 3 | Add Redis caching for likes count
PHASE 4: MessagingService
34 | 4 | Implement message request logic
35 | 4 | Accept/decline message requests
36 | 4 | Setup WebSocket for real-time messaging
37 | 4 | Track online/offline user status
PHASE 5: JobService (MOST IMPORTANT)
38 | 5 | Implement recruiter registration flow
39 | 5 | Implement job posting API
40 | 5 | Enable resume PDF upload
41 | 5 | Store resumes in S3 / local storage
42 | 5 | Send resume to AI service for processing
43 | 5 | Extract skills, experience & location from resume
44 | 5 | Implement job matching algorithm
45 | 5 | Calculate skills match percentage
PHASE 6: Automated Job Scraping
46 | 6 | Create company database
47 | 6 | Store company career page URLs
48 | 6 | Implement scheduler for daily scraping
49 | 6 | Scrape career pages
50 | 6 | Parse job title, location & JD
51 | 6 | Normalize and deduplicate job data
PHASE 7: Notifications
52 | 7 | Implement notification service
53 | 7 | Send job match alerts
54 | 7 | Send message notifications
PHASE 8: Frontend (Tailwind)
55 | 8 | Build login & registration UI
56 | 8 | Build user profile UI
57 | 8 | Build feed UI
58 | 8 | Build messaging UI
59 | 8 | Build jobs dashboard

## Required info
Architecture | Tech Stack | Microservices | Phases | Phases | Tracker | Assignee | Remarks
| Backend Java 17 Spring Boot 3 Spring Security + JWT Spring Cloud (Gateway, Eureka, Config) Spring Data JPA Spring Scheduler WebSocket (Messaging) Frontend Tailwind CSS Thymeleaf (initial) Later: React / Angular (optional) Database PostgreSQL (recommended) Redis (cache + rate limiting) Messaging / Events Kafka (ideal) or RabbitMQ AI / NLP Python microservice (FastAPI) spaCy / Sentence Transformers Resume → Keyword extraction | api-gateway | PHASE 1: Foundation (MUST DO FIRST) Step 1: Project Setup Create parent Maven project Add modules: api-gateway config-server service-registry user-service post-service message-service job-service Step 2: Config Server Centralize application.yml Use Git-based config repo Step 3: Service Registry Eureka Server Register all services 🔹 PHASE 2: UserService (Heart of System) Step 4: User Auth Register Login JWT generation Password encryption (BCrypt) Step 5: OAuth Google OAuth Map OAuth user → local user Step 6: RBAC Roles table Role mapping Step 7: Connections Send request Accept / Reject Connection graph 🔹 PHASE 3: PostService Step 8: Post CRUD Create post Fetch feed (based on connections) Privacy filter Step 9: Like / Comment Optimistic updates Redis caching for likes count 🔹 PHASE 4: MessagingService Step 10: Messaging Logic Message requests Accept / decline Step 11: WebSocket Real-time messaging Online/offline status 🔹 PHASE 5: JobService (🔥 MOST IMPORTANT) Step 12: Recruiter Flow Recruiter registration Job posting Step 13: Resume Upload PDF upload Store in S3 / local Step 14: AI Resume Processing Send resume to AI service Extract: Skills Experience Location Keywords Step 15: Job Matching Engine Compare: Skills match % Location preference Experience 🔹 PHASE 6: Automated Job Scraping (USP) Step 16: Company DB Store company name + career page URL Step 17: Scheduler Daily cron job Scrape career pages Parse: Job title Location JD Step 18: Store Jobs Avoid duplicates Normalize data 🔹 PHASE 7: Notifications Step 19: Notification Service Job match alerts Message notifications 🔹 PHASE 8: Frontend (Tailwind) Step 20: UI Pages Login / Register Profile Feed Messaging Jobs dashboard | PHASE 1: Foundation (MUST DO FIRST)
|  | config-server |  | Step 1: Project Setup |  | Abhijeet
|  | service-registry |  | Create Repo | Done
|  | user-service |  | Add modules:
|  | post-service |  | api-gateway | Done
|  | message-service |  | config-server
|  | job-service |  | service-registry | Done
|  |  |  | user-service | Done
post-service
message-service
job-service
|  |  |  | Step 2: Config Server |  | Abhijeet | As of now we are using application.properties for each services for better control, we will set it up once all services are tested
Centralize application.yml
Use Git-based config repo
Step 3: Service Registry
|  |  |  | Eureka Server | Done
|  |  |  | Register all services | Done
🔹 PHASE 2: UserService (Heart of System)
|  |  |  | Step 4: User Auth |  | Abhijeet
|  |  |  | Register | Done
|  |  |  | Login | Done
|  |  |  | JWT generation | Done
|  |  |  | Password encryption (BCrypt) | Done
|  |  |  | Step 5: OAuth |  | Abhijeet
|  |  |  | Google OAuth | in progress |  | Code is written will be validated and tested after Ui is available
|  |  |  | Map OAuth user → local user | in progress
|  |  |  | Phase 2A: User Profile Enhancement. |  | Abhijeet
|  |  |  | In User Details, add Experience, Education, Certifications, User profile details | Done
|  |  |  | Crud operations | Done
|  |  |  | Implement in Services | in progress
|  |  |  | API exposed to update all details and showcase when we show userdetails | in progress
Step 6: RBAC
Roles table
Role mapping
Step 7: Connections
Send request
Accept / Reject
Connection graph
🔹 PHASE 3: PostService
Step 8: Post CRUD
Create post
Fetch feed (based on connections)
Privacy filter
Step 9: Like / Comment
Optimistic updates
Redis caching for likes count
🔹 PHASE 4: MessagingService
Step 10: Messaging Logic
Message requests
Accept / decline
Step 11: WebSocket
Real-time messaging
Online/offline status
🔹 PHASE 5: JobService (🔥 MOST IMPORTANT)
Step 12: Recruiter Flow
Recruiter registration
Job posting
Step 13: Resume Upload
PDF upload
Store in S3 / local
Step 14: AI Resume Processing
Send resume to AI service
Extract:
Skills
Experience
Location
Keywords
Step 15: Job Matching Engine
Compare:
Skills match %
Location preference
Experience
🔹 PHASE 6: Automated Job Scraping (USP)
Step 16: Company DB
Store company name + career page URL
Step 17: Scheduler
Daily cron job
Scrape career pages
Parse:
Job title
Location
JD
Step 18: Store Jobs
Avoid duplicates
Normalize data
🔹 PHASE 7: Notifications
Step 19: Notification Service
Job match alerts
Message notifications
🔹 PHASE 8: Frontend (Tailwind)
Step 20: UI Pages
Login / Register
Profile
Feed
Messaging
Jobs dashboard